## Conformed Contract
Revisions
[7 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11
Files Included in Conformed Contract | [5 empty] | Executed Contract | change | date | change | date | change | date | change | date | change | date | change | date | change | date | change | date | change | date | change | date | change | date
Book 1 | [5 empty] | 2006-12-26
1 | Book 1 Contract |  |  |  |  | 2006-12-26 | CO 001 | 2007-01-12 | EBCP 008 | 2007-04-14 | EBCP 056 | 2008-06-05
1 | Book 1 Exhibit A Acronyms and Definitions |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit B Completion Deadlines |  |  |  |  | 2006-12-26 | CO 008 | 2007-04-19 | CO 022 | 2007-08-16 | CO 025 | 2007-09-07 | CO 039 | 2007-12-06 | EBCP 043 | 2007-11-29 | EBCP 046 | 2008-01-16 | EBCP 047 | 2008-01-29 | CO 063 | 2008-09-11 | EBCP 061 | 2008-09-24 | CO 067 | 2008-10-16 | EBCP 064 | 2009-03-31
1 | Book 1 Exhibit C Federal Requirements |  |  |  |  | 2006-12-26 | EBCP 049 | 2008-01-18
1 | Book 1 Exhibit C Federal Requirements- Attachment 1 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit C Federal Requirements- Attachment 2 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit C Federal Requirements- Attachment 3 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit C Federal Requirements- Attachment 4 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit C Federal Requirements- Attachment 5.pdf | [5 empty] | EBCP 049 | 2008-01-18
1 | Book 1 Exhibit C Federal Requirements- Attachment 6.pdf | [5 empty] | EBCP 049 | 2008-01-18
1 | Book 1 Exhibit D DBE Provisions |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit D DBE Provisions-Form 1 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit D DBE Provisions-Form 2.pdf |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit D DBE Provisions-Form 3 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit D DBE Provisions-Form 4a |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit D DBE Provisions-Form 4b affidavit.pdf |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit E Key Personnel |  |  |  |  | 2006-12-26 | EBCP 001 | 2007-02-08
1 | Book 1 Exhibit F Performance Bond |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit G Payment Bond |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit H Settlement of Claims |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit H Settlement of Claims-Attachment 1 |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit I Letter of Vested Interest |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit J Equal or Better Change Proposal Form |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit K VECP Sample Calculation |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit L Cost Analysis for Request for Change Order |  |  |  |  | 2006-12-26
1 | Book 1 Exhibit M Dispute Resolution Board Agreement |  |  |  |  | 2006-12-26
Book 2 | [5 empty] | 2006-12-26
2 | Book 2 Sec 01 Configuration Requirements |  |  |  |  | 2006-12-26
2 | Book 2 Sec 02 Project Management |  |  |  |  | 2006-12-26 | EBCP 051 | 2008-03-31
2 | Book 2 Sec 03 Quality Management |  |  |  |  | 2006-12-26
2 | Book 2 Sec 04 Public Information |  |  |  |  | 2006-12-26
2 | Book 2 Sec 05 Environmental |  |  |  |  | 2006-12-26 | CO 021 | 2007-08-17 | CO 049 | 2008-04-21
2 | Book 2 Sec 06 Third Party Agreements |  |  |  |  | 2006-12-26 | EBCP 035 | 2007-09-24
2 | Book 2 Sec 07 Utilities |  |  |  |  | 2006-12-26 | EBCP 005 | 2007-03-21
2 | Book 2 Sec 07 Utilities-Exhibit A |  |  |  |  | 2006-12-26
2 | Book 2 Sec 08 Right of Way |  |  |  |  | 2006-12-26 | EBCP 056 | 2008-06-05
2 | Book 2 Sec 09 Survey |  |  |  |  | 2006-12-26
2 | Book 2 Sec 10 Geotech |  |  |  |  | 2006-12-26
2 | Book 2 Sec 11 Signing Pvt Marking & Lighting |  |  |  |  | 2006-12-26 | EBCP 017 | 2007-05-22 | EBCP 038 | 2007-10-05
2 | Book 2 Sec 12 Drainage |  |  |  |  | 2006-12-26
2 | Book 2 Sec 13 Roadways & Pavements |  |  |  |  | 2006-12-26 | EBCP 045 | 2008-01-17 | EBCP 058 | 2008-04-25
2 | Book 2 Sec 13 Roadways & Pavements-Exhibit A.pdf | [5 empty] | EBCP 058 | 2008-04-25
2 | Book 2 Sec 14 Signals & ITS |  |  |  |  | 2006-12-26 | EBCP 038 | 2007-10-05
2 | Book 2 Sec 15 Structures |  |  |  |  | 2006-12-26 | EBCP 004 | 2007-03-13
2 | Book 2 Sec 16 Urban Design |  |  |  |  | 2006-12-26
2 | Book 2 Sec 17 MOT |  |  |  |  | 2006-12-26
2 | Book 2 Sec 18 Maintenance during Construction |  |  |  |  | 2006-12-26
Book 3 | [5 empty] | 2006-12-26
3 | Book 3a Applicable Standards.doc |  |  |  |  | 2006-12-26
3 | Book 3b Additional Applicable Standards.xls |  |  |  | updated when changes are made to Book 3 | 2006-12-26 | EBCP 023 | 2007-06-12
3 | Provided Documents for Book 3 |  |  |  |  | 2006-12-26
3 |  | GC AAS 01-01B Sec 0303 rev 2.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-01B PDF 6-02 EBCP 033 rev3.pdf |  |  |  |  | EBCP 033 | 2007-09-06
3 |  | GC AAS 01-02C Sec 0304 rev3.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-03 Sec 0501 rev3.doc |  |  |  | 2006-12-26 | deleted | 2007-05-31
3 |  | GC AAS 01-03 Sec 0501 EBCP 018 rev4.pdf |  |  |  |  | EBCP 018 | 2007-05-31 | deleted | 2007-08-30
3 |  | GC AAS 01-03 Sec 0501 EBCP 034 rev5.pdf |  |  |  |  | EBCP 034 | 2007-08-30 | deleted | 2008-03-07
3 |  | GC AAS 01-03 Sec 0501 EBCP 050 rev6.pdf |  |  |  |  | EBCP 050 | 2008-03-07
3 |  | GC AAS 01-04C Sec0502 rev3.doc |  |  |  | 2006-12-26 | deleted | 2007-05-31
3 |  | GC AAS 01-04C Sec0502 EBCP 019 rev4.pdf |  |  |  |  | EBCP 019 | 2007-05-31 | deleted | 2007-11-15
3 |  | GC AAS 01-04C Sec0502 EBCP 041 rev5.pdf |  |  |  |  | EBCP 041 | 2007-11-15 | deleted | 2008-03-07
3 |  | GC AAS 01-04C Sec0502 EBCP 050 rev6.pdf |  |  |  |  | EBCP 050 | 2008-03-07
3 |  | GC AAS 01-05B Sec0506 rev2.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-07A Sec0206a rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-08B Sec0701a rev2.doc |  |  |  | 2006-12-26 | deleted | 2007-06-14
3 |  | GC AAS 01-08B EBCP 025 Sec0701a rev3.doc |  |  |  |  | EBCP 025 | 2007-06-14
3 |  | GC AAS 01-09A Sec0703 rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-10 Sec0704 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-11 Sec0711 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-12 Sec0717 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 01-13 Sec1010 rev0.doc |  |  |  | 2006-12-26 | deleted | 2007-04-11
3 |  | GC AAS 01-13 Sec1010 EBCP 014 rev1.pdf |  |  |  |  | EBCP 014 | 2007-04-11 | deleted | 2008-04-11
3 |  | GC AAS 01-13a Sec1010 EBCP 052 rev2.pdf |  |  |  |  | EBCP 052 | 2008-04-11
3 |  | GC AAS 01-14 Sec0720a EBCP 014 rev0.pdf |  |  |  |  | EBCP 014 | 2007-04-11 | deleted | 2007-07-20
3 |  | GC AAS 01-14 Sec0720a EBCP 014 rev1.pdf |  |  |  |  | EBCP 027 | 2007-07-20 | deleted | 2008-04-11
3 |  | GC AAS 01-14b Sec0720 EBCP 052 rev3.pdf |  |  |  |  | EBCP 052 | 2008-04-11
3 |  | GC AAS 01-15 Sec0702 EBCP 021 rev0.pdf |  |  |  |  | EBCP 021 | 2007-05-31 | deleted | 2007-08-16
3 |  | GC AAS 01-15 Sec0702 EBCP 032 rev1.pdf |  |  |  |  | EBCP 032 | 2007-08-16 | deleted | 2007-12-18
3 |  | GC AAS 01-15 Sec0702 EBCP 044 rev2.pdf |  |  |  |  | EBCP 044 | 2007-12-18 | deleted | 2008-08-14
3 |  | GC AAS 01-15 Sec0702 EBCP 059 rev4.pdf |  |  |  |  | EBCP 059 | 2008-08-14
3 |  | GC AAS 01-16 Sec0617 EBCP 028 rev0.pdf |  |  |  |  | EBCP 028 | 2007-07-20
3 |  | GC AAS 01-16 Sec0712 EBCP 031 rev0.pdf |  |  |  |  | EBCP 031 | 2007-08-16
3 |  | GC AAS 01-18 Sec1059 EBCP 020 rev2.pdf |  |  |  |  | EBCP 020 | 2007-05-31
3 |  | GC AAS 01-19 PAL/Qual. Lists EBCP 029 rev0.pdf |  |  |  |  | EBCP 029 | 2007-07-20
3 |  | GC AAS 01-21 Sec0605 EBCP 037 rev0.pdf |  |  |  |  | EBCP 037 | 2007-09-28
3 |  | GC AAS 01-22 Sec0206 EBCP 039 rev0.pdf |  |  |  |  | EBCP 039 | 2007-10-19
3 |  | GC AAS 01-23 Sec1049 EBCP 048 rev0.pdf |  |  |  |  | EBCP 048 | 2008-02-20
3 |  | GC AAS 01-24 Sec1005 EBCP 050 rev1.pdf |  |  |  |  | EBCP 050 | 2008-03-07
3 |  | GC AAS 01-25 Sec1029 EBCP 054 rev0.pdf |  |  |  |  | EBCP 054 | 2008-03-24
3 |  | GC AAS 01-26 Sec0203 EBCP 060 rev0.pdf |  |  |  |  | EBCP 060 | 2008-09-03
3 |  | GC AAS 02-01 EBCP 055 rev0.pdf |  |  |  |  | EBCP 055 | 2008-05-12
3 |  | GC AAS 03-01A rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 03-02 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 03-05 part1 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 03-05 part2 rev0.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 03-6B EBCP 062 rev0.pdf |  |  |  |  | EBCP 062 | 2009-02-01
3 |  | GC AAS 03-08A EBCP 063 rev0.pdf |  |  |  |  | EBCP 063 | 2009-02-01
3 |  | GC AAS 03-09 rev0.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 03-10 rev0.pdf |  |  |  | 2006-12-26 | deleted | 2007-04-24
3 |  | GC AAS 03-10 EBCP 009 rev1.pdf |  |  |  |  | EBCP 009 | 2007-04-24
3 |  | GC AAS 03-11 rev0.pdf |  |  |  |  | EBCP 016 | 2007-05-17
3 |  | GC AAS 03-12 rev0.pdf |  |  |  |  | EBCP 024 | 2007-06-12
3 |  | GC AAS 03-13 EBCP 028 Project Barrier rev0.pdf |  |  |  |  | EBCP 028 | 2007-07-20
3 |  | GC AAS 03-14 Std. Plan 609.00N rev0.pdf |  |  |  |  | EBCP 026 | 2007-06-21
3 |  | GC AAS 04-01 4-04 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 04-02 4-04.1 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 04-03 4-06 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 04-04A 4-07 rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 04-05 attachment.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 04-06 EBCP 006 rev0.pdf |  |  |  |  | EBCP 006 | 2007-03-21
3 |  | GC AAS 05-01A 6-03 rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 05-02 6-04 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 06-01 rev0.xls |  |  |  | 2006-12-26
3 |  | GC AAS 06-02 rev0.xls |  |  |  | 2006-12-26
3 |  | GC AAS 06-03A rev1.xls |  |  |  | 2006-12-26
3 |  | GC AAS 06-04 rev0.xls |  |  |  | 2006-12-26
3 |  | GC AAS 06-05 Attachment - Caltrans SDC.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 06-05 rev0.xls |  |  |  | 2006-12-26
3 |  | GC AAS 06-06 rev0.xls |  |  |  | 2006-12-26
3 |  | GC AAS 06-07 EBCP 003 rev0.pdf |  |  |  |  | EBCP 003 | 2007-03-21
3 |  | GC AAS 06-08 EBCP 010 rev0.pdf |  |  |  |  | EBCP 010 | 2007-04-24 | deleted | 2007-07-23
3 |  | GC AAS 06-08 EBCP 030 rev1.pdf |  |  |  |  | EBCP 030 | 2007-07-23
3 |  | GC AAS 06-09 EBCP 012 rev0.pdf |  |  |  |  | EBCP 012 | 2007-04-24
3 |  | GC AAS 06-10 EBCP 013 rev0.pdf |  |  |  |  | EBCP 013 | 2007-04-24
3 |  | GC AAS 06-11 EBCP 011 rev0.pdf |  |  |  |  | EBCP 011 | 2007-04-24
3 |  | GC AAS 06-12 EBCP 027 rev0.pdf |  |  |  |  | EBCP 027 | 2007-07-20
3 |  | GC AAS 06-13 EBCP 042 rev0.pdf |  |  |  |  | EBCP 042 | 2007-11-16
3 |  | GC AAS 08-01A 8-01 rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 08-02 Figure 8-1 rev0.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 09-01A 9-07 rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 09-02 EBCP 007 rev0.pdf |  |  |  |  | EBCP 007 | 2007-03-21
3 |  | GC AAS 09-02 EBCP 022 rev0.pdf |  |  |  |  | EBCP 022 | 2007-05-31
3 |  | GC AAS 10-01 8-02 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 10-01 rev0 part1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 10-01 rev0 part2.doc |  |  |  | 2006-12-26
3 |  | GC AAS 10-02 Figure 8-02 rev0.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 10-03 EBCP 063 rev0.pdf |  |  |  |  | EBCP 063 | 2009-02-01
3 |  | GC AAS 11-01 attachment.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 11-01 section 8-03 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 11-02 figure 8-03 rev0.doc |  |  |  | 2006-12-26
3 |  | GC AAS 11-03A section 8-05 rev1.doc |  |  |  | 2006-12-26
3 |  | GC AAS 11-04 figure 8-05 rev0.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 11-05 EBCP 062 rev0.pdf |  |  |  |  | EBCP 062 | 2009-02-01
3 |  | GC AAS 12-1a EBCP 053 rev0.pdf |  |  |  |  | EBCP 053 | 2008-05-07
3 |  | GC AAS 13-01 thru 25-01.pdf |  |  |  | 2006-12-26
3 |  | GC AAS 26-01B Draft Urban Design Plans.pdf |  |  |  | 2006-12-26 | deleted | 2007-08-17
4 |  | GC AAS 26-01C Draft Urban Design Plans.pdf |  |  |  |  | CO 021 | 2007-08-17
Book 4 | [5 empty] | 2006-12-26
4 | Book 4 Contract Drawings Data Reports.doc |  |  |  |  | 2006-12-26
4 | Provided Documents for Book 4 |  |  |  |  | 2006-12-26
4 |  | Asbestos & Heavy Metal Paint Inspections |  |  |  | 2006-12-26
4 |  |  | 1050_FOREST_S254C.dgn |  |  | 2006-12-26
4 |  |  | 1334_highland_b259_J6I0978E_i010.dgn |  |  | 2006-12-26
4 |  |  | 25_northcote_B109_J6I0978E_i010.dgn |  |  | 2006-12-26
4 |  |  | 27_northcote_B113_J6I0978E-i010.dgn |  |  | 2006-12-26
4 |  |  | 8577_EVERETT_a235_J6I0978F_i010.dgn |  |  | 2006-12-26
4 |  | Certified Subsurface Utility Engineering Plans |  |  |  | 2006-12-26
4 |  |  | UtilitySurveyData.rsc |  |  | 2006-12-26
4 |  |  | UtilitySurveyData_Accuracy_Level_A_J6I0978.dgn |  |  | 2006-12-26
4 |  |  | UtilitySurveyData_Accuracy_Level_B_J6I0978.dgn |  |  | 2006-12-26
4 |  | Early Utility Relocations |  |  |  | 2006-12-26
4 |  |  | UIS-04-06.general construction notes.pdf |  |  | 2006-12-26
4 |  |  | UIS-04-06.plan and profile.pdf |  |  | 2006-12-26 | deleted | 2007-03-21
4 |  |  | UIS-04-06.revised plan and profile.pdf |  |  |  | EBCP 005 | 2007-03-21
4 |  |  | UIS-04-06.special construction notes.pdf |  |  | 2006-12-26
4 |  |  | UIS-05-78.dgn |  |  | 2006-12-26
4 |  |  | UIS-17-01.dgn |  |  | 2006-12-26
4 |  | Geotechnical Data |  |  |  | 2006-12-26
4 |  |  | Geotechnical Data Spring 2006 |  |  | 2006-12-26
4 |  |  |  | B-01 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-02 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-03 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-04 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-05 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-06 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-07 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-08 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-09 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-10 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-11 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-12 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-13 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-14 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-15 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-16 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-17 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-18 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-19 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-20 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-21 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-22 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-23 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-24 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-25 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-26 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-28 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-29 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-30 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-31 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-32 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-33 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-34 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-35 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-36 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-37 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-38 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-39 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-40 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-41 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-42 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-43 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-44 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-46 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-47 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-48 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-49 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-50 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | B-51 Rev xy.pdf |  | 2006-12-26
4 |  |  |  | Boring_Locations_8db_Spring2006.dgn |  | 2006-12-26
4 |  |  | Geotechnical Data locations - coordinates.zip (3 files) |  |  | 2006-12-26
4 |  |  | Geotechnical Data locations_updated.zip (3 files) |  |  | 2006-12-26
4 |  |  | GreenwayPBS - updated |  |  | 2006-12-26
4 |  |  | greenwaypgr_updated.pdf |  |  | 2006-12-26
4 |  |  | GreenwayPrepgr (1 file) |  |  | 2006-12-26
4 |  |  | ParkwayPBS - updated |  |  | 2006-12-26
4 |  |  | parkwaypgr_updated.pdf |  |  | 2006-12-26
4 |  |  | ParkwayPrepgr (1 file) |  |  | 2006-12-26
4 |  |  | s254c005.tif |  |  | 2006-12-26
4 |  |  | ThruwayPBS - updated |  |  | 2006-12-26
4 |  |  | thruwaypgr_updated.pdf |  |  | 2006-12-26
4 |  |  | thruwayPrepgr (1 file) |  |  | 2006-12-26
4 |  | Land Survey Monumentation |  |  |  | 2006-12-26
4 |  |  | Horizontal and Vertical Control Points 2006.xls |  |  | 2006-12-26
4 |  |  | Horizontal and Vertical Control Points 2006.dgn |  |  | 2006-12-26
4 |  | Master Utility Agreements |  |  |  | 2006-12-26
4 |  |  | Ameren |  |  | 2006-12-26
4 |  |  |  | Executed Ameren MUA 2006-09-18.pdf |  | 2006-12-26
4 |  |  | City of St. Louis |  |  | 2006-12-26
4 |  |  |  | St Louis City Municipal Agreement Exhibit B MUA.doc |  | 2006-12-26
4 |  |  | Laclede Gas |  |  | 2006-12-26
4 |  |  |  | Laclede MUA 2006-12-18.doc |  | 2006-12-26 | deleted | 2007-05-15
4 |  |  |  | Laclede MUA Exhibits 2006-09-22.pdf |  | 2006-12-26 | deleted | 2007-05-15
4 |  |  |  | Executed Laclede MUA 2007-05-15.pdf |  |  | EBCP 015 | 2007-05-15
4 |  |  | LightCore |  |  | 2006-12-26
4 |  |  |  | Executed LightCore MUA 2006-07-25.pdf |  | 2006-12-26 | EBCP 057 | 2008-07-03
4 |  | MSD Agreement |  |  |  | 2006-12-26
4 |  |  | MSD Agreement - Draft 2006-07-14.doc |  |  | 2006-12-26 | deleted | 2007-03-02
4 |  |  | MSD Agreement - Executed 2006-11-09.pdf |  |  | 2007-03-02 | EBCP 002 | 2007-03-02
4 |  | Municipal Seprate Storm Sewer System (MS4) Permit |  |  |  | 2006-12-26
4 |  |  | DNR - State Operating Permit - Water pollution Control Program.pdf |  |  | 2006-12-26
4 |  |  | Storm Water Management Plan 2006-07-21.pdf |  |  | 2006-12-26
4 |  | Right of Way CADD Files |  |  |  | 2006-12-26
4 |  |  | New_ROW_I-64_8db |  |  | 2006-12-26
4 |  |  | stripmap_Ex_Row.dgn |  |  | 2006-12-26
4 |  | Traffic Counts and Forecasts |  |  |  | 2006-12-26
4 |  |  | Truck Traffic Counts by Class 2006 24hr counts.xls |  |  | 2006-12-26
4 |  |  | yr2001 I64 arterial counts AM PM.pdf |  |  | 2006-12-26
4 |  |  | yr2001 I64 counts.GW.pdf |  |  | 2006-12-26
4 |  |  | yr2001 I64 counts.PW.pdf |  |  | 2006-12-26
4 |  |  | yr2001 I64 counts.TW.pdf |  |  | 2006-12-26
4 |  |  | yr2002 MoDOT D6 Traffic map.pdf |  |  | 2006-12-26
4 |  |  | yr2020 I64 build forecasts AM PM.pdf |  |  | 2006-12-26
4 |  | Verified Utility Information |  |  |  | 2006-12-26
4 |  |  | Test_Holes.dgn |  |  | 2006-12-26
4 |  |  | Test_Holes - Data Sheets |  |  | 2006-12-26
4 |  |  | Verified Utility Information Summary Sheet |  |  | 2006-12-26
4 |  | Access Justification Report Guidelines |  |  |  | 2006-12-26
4 |  | Approved Design Exception |  |  |  | 2006-12-26
4 |  | Approved Design Exceptions submitted by Gateway Constructors |  |  |  | 2006-12-26
4 |  | Condemnation Document Submittal Checklist |  |  |  | 2006-12-26
4 |  | Historic Preservation Sec 106 Programmatic Agreement |  |  |  | 2006-12-26
4 |  | Load Rating for Design-Build Bridges |  |  |  | 2006-12-26
4 |  | Right of Way Condemnation Guidelines.zip |  |  | (3 files) | 2006-12-26
4 |  | Right of Way Procedures Manual |  |  |  | 2006-12-26
4 |  | Right of Way Relocation Manual |  |  |  | 2006-12-26
4 |  | Right of Way Schedule 2006-12-15 |  |  |  | 2006-12-26 | updates sent monthly
4 |  | Right of Way Special Conditions 2006-09-19 |  |  |  | 2006-12-26 | combined with Right of Way Schedule
4 |  | Traffic Noise Measurement Data - Existing |  |  |  | 2006-12-26
4 |  | USACE 404 Permit and Approved Jurisdictional Determination 2006-09-07.pdf |  |  |  | 2006-12-26
4 |  | Work Breakdown Structure |  |  |  | 2006-12-26
P | Proposal Documents |  |  |  |  | 2006-12-26
P |  | GC Final - Part 1 General Information.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 2 Draft DBE Performance Plan.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 3 AAS.pdf |  |  |  | 2006-12-26 | EBCP 028 | 2007-07-20
P |  | GC Final - Part 4 Technical 3.6.1 Schedule.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a Geometrics.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a-dwgs 1 of 6.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a-dwgs 2 of 6.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a-dwgs 3 of 6.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a-dwgs 4 of 6.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a-dwgs 5 of 6.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2a-dwgs 6 of 6.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2b Pavements.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.2c Structures.pdf |  |  |  | 2006-12-26 | EBCP 036 | 2007-09-24
P |  | GC Final - Part 4 Technical 3.6.3 MOT 1 of 4.pdf |  |  |  | 2006-12-26 | EBCP 061 | 2008-09-24 | CO 067 | 2008-10-16
P |  | GC Final - Part 4 Technical 3.6.3 MOT 2 of 4.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.3 MOT 3 of 4.pdf |  |  |  | 2006-12-26 | EBCP 040 | 2007-11-15
P |  | GC Final - Part 4 Technical 3.6.3 MOT 4 of 4.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.3-dwgs MOT 1 of 2.pdf |  |  |  | 2006-12-26 | EBCP 047 | 2008-01-29
P |  | GC Final - Part 4 Technical 3.6.3-dwgs MOT 2 of 2.pdf |  |  |  | 2006-12-26 | EBCP 046 | 2008-01-16 | EBCP 064 | 2009-03-31
P |  | GC Final - Part 4 Technical 3.6.4 PI.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 4 Technical 3.6.5 DBE Workforce.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 5 Administrative 1 of 4.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 5 Administrative 2 of 4.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 5 Administrative 3 of 4.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 5 Administrative 4 of 4.pdf |  |  |  | 2006-12-26
P |  | GC Final - Part 6 Price Allocation.pdf |  |  |  | 2006-12-26