## Sheet1
REVISED 4/26/2002
CONSTRUCTABILITY CHECKLIST |  | Reviewer |  |  | Signature
Project No. |  | Designer
Job No. |  | PM
Route: |  | RE
County: |  | AE
A. | SITE INVESTIGATION | YES | NO | N/A | COMMENT
1 | Field investigation completed to ensure actual field conditions are reflected on the plans and in the design including pavement and bridge conditions.
2 | Existing site surveyed and horizontal and vertical controls established.
3 | Subsurface exploration completed.
4 | Utility investigation completed with utility companies listed including contacts and phone numbers.
5 | Underground utility depths are adequate at stream crossings and in entrance cuts in the backslope areas.
6 | USGS has been notified of all survey monuments that will be disturbed.
7 | All overhead restrictions such as utility lines in areas where cranes will be used have been identified.
8 | Underground utilities that remain in-place are clearly marked as to location and depth.
9 | Current ADT,including peak hourly volumes, has been checked for accuracy and potential construction problems.
10 | Locations where guardrail and/or sign post/bases are clear of underground utilities.
11 | All water wells that need plugged are indicated on the plans.
12 | Stockpile/Plant sites on the project were considered for large paving projects.
B. | EARTHWORK | YES | NO | N/A | COMMENT
1 | Haul road widths are designed to allow two-way truck/scraper traffic.
2 | Interception ditches are provided at the top of cuts to minimize erosion and slides.
3 | Shoulder widening provided at guardrail locations.
4 | All evidence or indication that rock will be encountered in Class 1, 2 or 3 excavation has been verified.
5 | Undergrading considered where existing ditches/ ponds/ poorly drained areas fall within roadway embankments.
6 | Consideration has been given to damages caused to houses and overhead utilities due to flying rock.
7 | Shrink and swell factors have been checked for accuracy.
8 | Any special fills such as bridge abutments are identified and material is provided.
9 | The economics of balancing the project was checked against the cost of borrow and/or wasting material.
10 | Balance location and staging favor the use of scrapers over dump trucking to move large quantities of material.
11 | Temporary stream crossings considered when balances dictate hauling across a river or stream.
12 | All unsuitable material is clearly identified.
13 | Earthwork volumes are balanced in each stage.
14 | Special access required such as haul roads to borrow sites, etc. have been considered.
15 | Overburden removed to access rock for fills, rock caps, etc. can be incorporated into the project and does not require stockpiling.
C. | BASES & PAVEMENT | YES | NO | N/A | COMMENT
1 | SP125 or similar mix is used in areas that require thin wedging.
2 | Thickness of pavement has been considered for overhead clearances when paving beneath bridges.
3 | Extra tonnage has been included for roughness on resurfacing projects that do not include coldmill profiling.
4 | Profile grades have been established on widening or major resurfacing projects that require curb and gutter construction.
5 | Concrete pavement repair where traffic lanes have to be opened at night can be completed between April and October.
6 | Additional tack is included on asphalt paving projects where stage construction requires exposure of sublayers for long periods.
7 | Joints in final pavement surface will coincide with finished lane lines.
8 | Concrete base widening considered in lieu of asphalt base in urban areas where entrances and irregular areas impact production rates.
9 | Concrete pavement repairs near ramp termini staged to allow turning movements for tractor trailers.
10 | Excessive wedging over existing pavement at connections is minimized.
11 | Saw joints for pavement repair includes quantities for sawing the longitudinal joints at center/lane lines
12 | The number of asphaltic mixes have been minimized.
13 | Allowances have been made for equipment widths,track lines, string lines,etc. when lanes are paved in stages or close to existing lanes.
D. | DRAINAGE | YES | NO | N/A | COMMENT
1 | Drainage patterns have been checked and impacts to property owners have been considered. Time of concentration remains unchanged.
2 | Drainage/ponding problems checked in all stages where open ditch drainage is being converted to a curb & gutter system.
3 | Pipe collars are provided for all dissimilar pipe connections.
4 | Special erosion control consideration has been considered on all balances over 17 acres.
5 | All islands and S-Curbs constructed along the R/W line will not pond water from property that drains toward the R/W.
6 | Erosion control is provided for all stages of work.
7 | All pavement, curb and gutter staging has been checked for drainage to prevent ponding problems.
8 | Vertical clearances between sewer lines and storm drainage pipes have been verified.
9 | Thick wall and broken back pipes considered for all high fill areas.
10 | Impacts of future urban development has been considered in stormwater design.
11 | Sediment basins have been considered.
12 | Temporary ditches and pipes are incorporated in each stage to allow runoff to occur.
E. | STRUCTURES | YES | NO | N/A | COMMENT
1 | Mechanical bar splices have been considered where exposed rebar required for lap splices interfere with traffic.
2 | There is sufficient room between the new alignment and the existing alignment to build the bridge without staging.
3 | Orientation of top slab reinforcement has been considered when removing headwalls from a skewed box culverts.
4 | Access to the bridge site by trucks carrying long girders has been considered.
5 | All span type bridges are located within tangent or full superelevation sections.
6 | Bridge staging is coordinated with roadway traffic control staging.
7 | End abutment fills in stage construction have been checked for shoring requirements.
8 | Borings were made within five foot of all proposed footings and end abutment locations.
9 | Bridge Division notified conduit for signals/lighting is required.
10 | Vertical clearances have been considered.
11 | Work pads have been considered for work in the stream.
12 | Bridges within the project limits have been checked for load limit restrictions.
D. | TRAFFIC CONTROL PLAN | YES | NO | N/A | COMMENT
1 | Overhead clearance for street lighting has been verified.
2 | Trenching for signal and lighting conduit does not interfere with the operation of existing signals or lighting.
3 | All city and county road closures have been identified and approved.
4 | Incident management considered to allow emergency vehicle travel through the detour/road closure/lane closure areas.
5 | Temporary surfacing considered when project is predicted to go through the winter months or local traffic must drive on unfinished grade.
6 | New signals can be constructed and placed in operation while existing signals remain in operation.
7 | Channelizers are provided for night work.
8 | Temporary guardrail has been considered near all steep slopes caused by staged construction.
9 | Heavy equipment/truck crossings over the existing alignment have been reviewed for safety such as sight distance.
10 | All signal controller locations have been approved by our signal electricians.
11 | All signal and lighting bases are located as to not interfere with sidewalks and wheelchair ramps.
12 | Locations where new alignment crosses the existing alignment can be constructed under traffic.
13 | Traffic control requirements realistic for site conditions.
14 | Lane widths in work zones, including bridges, are adequate.
15 | All lane closures are reasonable for traffic volumes and penalty for closure is provided for when required.
16 | Provisions have been made for pedestrian traffic.
17 | Sufficient signing and striping has been provided for all stages and are 350 compliant.
18 | Power source is available for temporary/permanent lighting, flashing barricades and signals.
19 | Existing signs to be removed and commission retained are clearly identified with storage location provided.
20 | Signal locations have been reviewed for sight distance and the presence of obstacles such as light poles, signs, etc.
21 | School buses, mail carriers and local traffic has been reviewed for special maintenance or traffic requirements.
22 | Detours have been considered to avert delays.
H. | MAINTENANCE CONSIDERATIONS | YES | NO | N/A | COMMENT
1 | All bridges and drainage structures are accessible for debris removal and channel cleanout.
2 | Manholes that fall within traffic lanes have bolt down type lids.
3 | Drain basins have been considered for all bridges.
4 | All drop-offs near sidewalks have handrails or fences to protect pedestrians.
5 | Maintenance has been notified of this project to allow time for surface repair, pipe replacements, etc.
6 | All ramp shoulders are designed to support tractor trailer parking.
7 | Wheelchair ramps provided at all sidewalk termini.
8 | All grates on drop inlets in urban areas are designed with bicycle bars.
9 | All permanent erosion control devices maintainable by maintenance forces.
I | JOB SPECIAL PROVISIONS/ PLANS | YES | NO | N/A | COMMENT
1 | Typical sections are provided for all pavement/shoulder transition areas.
2 | All entrances and side road connections have less than 10% and 5% slopes respectively.
3 | The radii on all commercial approaches will allow tractor trailer movement.
4 | All R/W in urban areas are mowable and sodded.
5 | Temporary median crossovers have been considered on dual lane roadways to shorten haul times.
6 | Areas requiring paving and/or milling are compatible with standard equipment sizes.
7 | Consideration has been given to clearing the utility corridor by separate contract to facilitate early relocation of utilities.
8 | All emergency or interim work needed before the contract is let has been identified.
9 | Field office/labs will be required.
10 | Details as shown on the plans can be constructed using standard equipment and operating procedures.
11 | All utility lines that cross the alignment have the vertical clearances required for earthmoving equipment to pass under at final profile grade.
12 | Blasting operations near fiber optic or gas lines have been reviewed by the appropriate utility company for shock wave damage.
13 | Utility relocation schedule checked for accuracy.
14 | All conflicts between JSP, standard specifications, and plan sheets have been eliminated.
15 | Small quantity bid items have been eliminated where possible.
16 | Small quantity bid items have been converted to Lump Sum bid units whenever possible.
J. | CONSTRUCTION STAGING | YES | NO | N/A | COMMENT
1 | Stages and balances will allow the availability of material/soil to build the finished subgrade.
2 | Construction staging will not require material to be hauled across/over the new pavement or provision for x-over made.
3 | Existing pavement to be removed can be incorporated into staged inslopes or disposal sites available within the project limits.
4 | Work has been phased to minimize the number of stages.
5 | Water drainage concerns due to coldmilling have been addressed.
6 | All Inslopes on stage construction are flatter than 1.5 to 1
7 | Staging has been checked for special conditions, such as slope stability, flooding due to ponding,spawning seasons, environmental concerns,etc.
8 | Private and commercial entrances accessible at all times on all stages.
9 | A check has been made to insure adjacent projects will not interfere.
K. | RIGHT OF WAY | YES | NO | N/A | COMMENT
1 | Sufficient R/W available for all operations.
2 | Sufficient easements available for all operations.
3 | All houses removed have been checked for asbestos removal.
4 | Fences that will require R/W staking prior to letting have been identified.
5 | All the negotiator's reports been reviewed for special requirements. Such as trees or shrubs to remain in-place and are clearly marked on the plans.
6 | Parcels/borrows with restricted access due to pending litigation, burial sites,springs or environmental concerns have been clearly marked.
7 | All ponds near the R/W that may be contaminated by silt from the project have been identified.
8 | Seed and mulch quantities are provided for all obliterated areas and borrows.
9 | All buried fuel tanks and environmental contamination sites have been investigated and disposal plans developed.
L | SCHEDULE | YES | NO | N/A | COMMENT
1 | Working days and productions rates for work items are reasonable.
2 | Construction sequence checked for accuracy..
3 | Consideration has been given for seasonal constraints.
4 | All regulatory permit restrictions such as working in a river or cutting trees have been clearly identified.
5 | Timing of letting facilitates fabrication of structural components such as bridge girders, pipes and precast culverts.
6 | Any restrictions on working hours have been identified.
7 | Any restrictions on work days such as no work on Holidays, weekends,Fridays or between 7:00am to 9:00am. have been identified.
8 | Project was considered for acceleration.
9 | Timing of letting facilitates material production such as aggregates for asphalt and concrete paving.
10 | Night and weekend work proposed, and impacts considered.