#### COST ESTIMATE GUIDE FOR RURAL PRELIMINARY DESIGN

(These cost figures were last updated on 3-15-04)

#### Cost-per-mile

[Cost-per-km]	Assumptions

New 2 Lane

Grading & Drainage	$650,000 [$405,000]	44 ft. [13.2 m] Roadbed

Base & Surface	$985,500 [$612,360]	Medium Duty PCCP

Add Lanes for Dual Lanes

Grading & Drainage	$575,000 [$360,000]	38 ft. [11.4 m] Roadbed

Base & Surface	 $858,900 [$533,700]	Medium Duty PCCP

$1,099,600 [$683,300]	Heavy Duty PCCP

### New 4 Lane

Grading & Drainage	$1,000,000 [$620,000]	2 - 38 ft. [11.4 m] Roadbed & Median

Base & Surface	$1,717,800 [$1,067,400]	Medium Duty PCCP

$2,199,100 [$1,366,500]	Heavy Duty PCCP

Outer Road

Grading & Drainage	$415,000 [$260,000]	28 ft. [8.4 m] Surface & 6 ft. [1.8 m] Shld.

Aggregate Surface	$108,300 [$67,300]

Paved Surface	$356,500 [$221,500]	28 ft. [8.4 m] Light Duty AC

8 in. [200 mm] Total AC thickness, 4 in. [100 mm] Type 5, 8 in. [200 mm] Ag. Shld.

Rehabilitation

8” Unbonded Concrete Overlay	$450,000 [$280,000]	38 ft. [11.4 m] Roadbed

1” Bondbreaker	$108,300 [$67,300]

Coldmilling <3 inches	$56,000 [$35,000]

12" Superpave Overlay	$543,800 [$337,900]

# Rubblization	$26,000 [$16,200]

Interchanges-Ramps Only, Excludes bridges and crossroad

- Diamond	Lump sum each

Grading & Drainage	$ 1,050,000

Base & Surface	$650,300

- Cloverleaf

Grading & Drainage	$2,110,000

Base & Surface	$1,626,400

Note:  Grading cost includes 30% Rock and assumes Medium Grading.

Grading Adjustment Factors

Light:  0.7;  Medium:  1.0;  Heavy:  3.0

Use these grading factors, unless justified with district information and proper documentation.

Miscellaneous and Utility Costs may be assumed to total 20 percent of the sum of grading & drainage, and surface & base, unless additional analysis is warranted.

Cost per	Cost per

Bridge Structures	Sq. foot	Sq. meter

Prestress Concrete	$60	$665

Steel Girder	$75	$835

Temporary Bridge (State furnished)	$45	$485

Temporary Bridge (Contractor furnished)	$125	$1345

Major Lake Crossing	$155	$1665

Major River Crossing	$180	$1940

- Percentage Cost Factors:

Bridge costs per square foot [square meter] should be increased for the following:

Item	% Increase

Stage Construction	10

Horizontal Curve Alignment	5

Seismic Category B*	15

Seismic Category C*	25

Seismic Category D*	40

Tight Site/Limited Access	10

* See Sheets 3 and 4 of this figure for details of seismic categories.

- For Stream Crossings:

Bridge Replacement Length = 1.25 X Existing Bridge Length, unless otherwise documented.  The existing bridge length can be obtained from TMS.

Bridge replacement length may be longer than 1.25 X Existing Bridge Length for bridges crossing FEMA regulatory floodways. Bridges on new alignments are required to span the entire floodway. For bridges on existing alignment, use 1.25 X Existing Bridge Length when the 100-year flood does not overtop the existing roadway. When the 100-year flood does overtop the existing roadway, the new bridge will be required to span the entire floodway.

- For Companion Grade Separation Structures:

Bridge Replacement Length = Existing Bridge Length.  The existing bridge length can be obtained from TMS.

Bridge Width should equal traveled way, shoulders and barrier rail width.

- Bridge Approaches:

The cost of bridge approaches should be added to the total cost derived from the approach slab area.  Bridge slab cost:

English:	($17/ft2) ( roadway width, ft) (25 ft.) (2)

Metric:	($182/m2) ( roadway width, m) (8.0 m) (2)

Cost per	Cost per

Bridge Removals	Sq. foot	Sq. meter

Simple Structures	$5	$55

Steel Structures over Roads	$7	$75

Concrete Structures over Interstates	$25	$280

(quick opening of lanes to traffic required)

Specialized Projects

Projects having unusual features and special scopes of work should be compared to similar types of district projects using historic data.  Generic cost information listed in this guide should not be applied for projects such as traffic signal improvements, geometric improvements, and other types of small projects.  Check with GHQ Design Bidding and Contract Services for assistance.

Additional costs should be included in the project estimate for retaining walls, extensive sound walls, temporary bypasses and traffic signals.